## week1
Computer Science 2 Project | Team Members: | Matunog, Mateo A.
Group Progress Report |  | Elardo, Allaina Marie A.
3rd Quarter
Week 1 - Jan 16, 2026 (covers week 1-3 of proj sched)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Make the "add expense" function. | The input is in a simple form and textbox. | Made function.
STRENGTH
Functional
Puts inputted data into a separate file
File can be altered in any way
AREAS FOR DEVELOPMENT
Make server to store history for when the file is deleted.
STRATEGY FOR SUCCESS
Make one or two function per week to finish the basics by the deadline.

## week2
Computer Science 2 Project | Team Members: | Matunog, Mateo A.
Group Progress Report |  | Elardo, Allaina Marie A.
3rd Quarter
Week 2 - Jan 23, 2026 (covers Week 4)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Create the history function to store recorded expenses. | Use a Float or Decimal type in our backend to handle cents/pennies accurately. | Created the history function.
STRENGTH
Lets the user view past expenses instead of only seeing the current balance.
AREAS FOR DEVELOPMENT
Live reload every purchase.
STRATEGY FOR SUCCESS
Make one or two function per week to finish the basics by the deadline.

## week3
Computer Science 2 Project | Team Members: | Matunog, Mateo A.
Group Progress Report |  | Elardo, Allaina Marie A.
3rd Quarter
Week 3 - Jan 30, 2026 (covers week 5)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Create balance function. | The function must be defined before the widget that uses it is created the code in the code, as the interpreter reads the script from top to bottom. | Created the balance function.
STRENGTH
Allows users to input their card balance as basis for purchases.
AREAS FOR DEVELOPMENT
Purchases aren't deducted from balance when added.
STRATEGY FOR SUCCESS
Make one or two functions per week to finish the basics by the deadline.

## week4
Computer Science 2 Project | Team Members: | Mateo, Matunog A.
Group Progress Report |  | Elardo, Allaina Marie A.
3rd Quarter
Week 4 - Feb 6, 2026 (covers week 6)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
To implement a delete feature that allows users to manage their expense records by removing selected entries or clearing all purchase history. | To make and use a function in Tkinter, you define a standard Python function and link it to a widget event, most commonly using a button's command option. | The function for the delete feature was created.
STRENGTH
A confirmation dialog helps prevent accidental deletion of all records.
The function handles cases where no item is selected, avoiding program crashes.
AREAS FOR DEVELOPMENT
There is no undo feature for deleted records.
STRATEGY FOR SUCCESS
Make one or two functions per week to finish the basics by the deadline.