## week1
Computer Science 2 Project | Team Members: | Matunog, Mateo A.
Group Progress Report |  | Elardo, Allaina Marie A.
3rd Quarter
Week 1 - Jan 16, 2026 (covers week 1-3 of proj sched)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Make the "add expense" function. | The input is in a simple form and textbox. | Made function.
STRENGTH
Functional
Puts inputted data into a separate file
File can be altered in any way
AREAS FOR DEVELOPMENT
Make server to store history for when the file is deleted.
STRATEGY FOR SUCCESS
Make one or two function per week to finish the basics by the deadline.

## week2
Computer Science 2 Project | Team Members: | Matunog, Mateo A.
Group Progress Report |  | Elardo, Allaina Marie A.
3rd Quarter
Week 2 - Jan 23, 2026 (covers Week 4)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Create the history function to store recorded expenses. | Use a Float or Decimal type in our backend to handle cents/pennies accurately. | Created the history function.
STRENGTH
Lets the user view past expenses instead of only seeing the current balance.
AREAS FOR DEVELOPMENT
Live reload every purchase.
STRATEGY FOR SUCCESS
Make one or two function per week to finish the basics by the deadline.

## week3
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 3 - Jan 30, 2026 (covers week 5)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week4
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 4 - Feb 6, 2026 (covers week 6)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
write at least 2 task
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS